**LIR COMMITTEE**

**24th October 2017**

**Board Room, Educampus Building, IFSC, Dublin**

**Present**: Peter Fleming, Breeda Herlihy, James Molloy, Peter Reilly, Clíona Ní Shúilleabháin. Jennifer Ball, Elaine Doherty, Glenn Wearen

**Apologies:** Ronan Kennedy, Jerald Cavanagh, Frank Brady, David Kane

|  |  |
| --- | --- |
| **Actions** | **Minutes** |
| **1: Minutes (11th Oct.)**  |
|  | Minutes of 11th October approved |
| **2: Alternative Feedback Working Group** |
|  | * JM demonstrated the free version of “Mentimeter” a discussion on best use of resource for Seminar followed
* **Action: JM to liase with treasurer if licensed version is required for purchase. JM to prepare how “Mentimeter” is introduced by speakers to Seminar attendees. To prepare a sample question.**
 |
| **3. LIR seminar 2017** |
|  | * **Full LIR Seminar 2017 Task list attached**
* **In addition:**
* JM clarified speaker name Lee O’Farrell for documentation
* **Action:BH to chase title from David Kane**
* **Action: BH to post Seminar Programme online**
* **Action:PR to send link to Horizon 2017 to LO’F as example of of data produced by libraries**
* **Action: PR to chase title for presentation from Lee O’Farrell, David White to chase David White for release, bio, photos**
* **Action:PR to send out email to list with link/registration details**
* **Action:PR to bring “Speaker Release” forms for Long Room Hub admin on Seminar Day.**
* **Action:PF to post Registration details online registration close date of midnight 17 Nov agreed.**
* **Action:PF/GW to add “carpentry” FAQ to pack**
* **Action: CnS: To circulate date for run through in Long Room Hub to Elaine, Glenn or his nominated Heanet rep.**
* **Action:JM to oversee Mentimeter on Seminar Day.**
* **Action:JB to create LAI CPD accreditation for seminar pack**
* **Action:GW to arrange av unit for Long Room Hub. To contact TCD tech to support wired connection in room on Seminar Day.**
* **Action GW; To ask for quote for catering for 70**
* **Action ED to chase Brendan Devlin for release, bio, photos.**
 |
|  |  |
| 4**.LIR AGM agenda** |
|  | * Constitutional amendments. Wording for three constitutional amendments discussed.
* Action GW: to contact LIR Members library directors with regard to obligations for membership of LIR cttee.
* Action: PR to circulate wording of amendments to cttee and to LIR list
* Election of officers will be discussed at meeting following AGM.
 |
| **5: Marking criteria for awarding LIR Bursary** |
|  | * PR lead a discussion. Three criteria for rating winning applications agreed. Bursary is increased to €800 and winners conference registration to be paid in advance by bursary was agreed.
* Action: PR to present agreed new criteria at AGM for voting
 |
| **7: AOB** |
|  |  |

|  |  |
| --- | --- |
| LIR Seminar 2017 Task List |  |
| Task | Responsible |
| Post Programme online (deadline 26th October) | Breeda |
| Registration goes live (deadline 26th October) \* | Peter Glenn |
| Room run through (10th November/TBC ) | Clíona, Elaine, Glenn |
| Liaising with speakers: release forms, biographies/pics, slides |   |
| Liaising with speakers: release forms, biographies/pics, slides | Chair Peter Reilly |
| LAI CPD certificate | Jennifer, Peter Reilly |
|   |   |
| Mentimeter online feedback (deadline ) | James |
| Print programmes (deadline ) | Peter Fleming |
| Print delegate list (deadline ) | Peter Fleming |
| Print biographies (deadline ) | Peter Fleming |
|  Print “Carpentry” promo/ FAQ |   |
| Close Registration (deadline 17th November, if not before) | Peter Fleming |
| Prepare Name Tags | Elaine Doherty |
|   |   |
| Bring Folders, pens, pull up Banner | Glenn |
| Prepare packs on seminar day (Start time 08.45) | Glenn & Peter to prep in advance |
| Liaise with caterers | Glenn |
| Tech Assistance/Presenter PC | Glenn, Clíona and LRH |
| Registration Desk | Peter, Cliona, Frank, Jennifer |
| Pull up banner | Glenn |
|  |   |
| Chairing morning | Peter Reilly  |
| Time keeping morning  | Elaine |
| Roving mike morning | Glenn |
| Twitter morning | Breeda |
|   |   |
| ~~Directions/ensuring delegates seated on time (afternoon)~~ |   |
| Chairing afternoon | Ronan |
| Time keeping afternoon | Peter |
| Roving mike afternoon | Cliona |
| Twitter afternoon | David Kane |
|  |  |
| \* Reg form: set limit and disable form at 100. Message to appear on site: 'Registration is now full.  |  |
| If you would like to add your name to our waiting list, please email glenn.wearen@heanet.ie |  |
|  |  |
|  |
|  |  |